## Sheet1
Lyft Eats Project Cost Estimate
Resources | Hourly Rate | Hours worked | Total Cost |  |  |  |  | WBS Totals
Project Manager | 46 | 50 | 2300 | Software Cost | # Units/Hrs. | Cost/Unit/Hr. | Subtotals
Analyst 1 | 74 | 25 | 1850
Analyst 2 | 78 | 25 | 1950 | Licensed software | 136 | 150 | 20400
Developer 1 | 136 | 35 | 4760 | Software development |  |  | 700000
Developer 2 | 136 | 35 | 4760 |  |  |  |  | 720400
Manager | 86 | 40 | 3440 | Full time Employee's Total Cost | 862 |  | 26615
Database Analyst | 21 | 25 | 525 |  |  |  |  | 26415
Tester 1 | 24 | 20 | 480 | Hardware
Tester 2 | 24 | 20 | 480 | Computers | 21 | 1000 | 21000
Tester 3 | 40 | 20 | 800 | Servers | 2 | 4000 | 8000
Deployment Team | 32 | 30 | 960 |  |  |  |  | 29000
Implementaion Team | 24 | 25 | 600 | Project Total |  |  |  | 775815
Marketing Analyst | 5 | 30 | 150
Analyst 3 | 8 | 25 | 200
Analyst 4 | 8 | 25 | 200
Accountant | 16 | 35 | 560
Deployment Member 1 | 72 | 25 | 1800
Deployment Member 2 | 8 | 25 | 200
Deployment Member 3 | 8 | 25 | 200
Deployment Member 4 | 8 | 25 | 200
| 854 | Total FTE: | 26415

## Staffing By FTEs (hidden)
XXX Project Staffing Plan
Prepared by: |  | Date:
Enter the number of FTEs by month for each role and/or add a line item for each resource
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
PLANNED
|  | Months | [11 empty] | Workdays | [12 empty] | Cost
|  | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Total
Resource/Role | Resource Cost/Hr | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Workdays | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Cost
Project Management
Project Manager | 125 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 228 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 19000 | 228000
Team Members | 75 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 228 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 136800
Software Development
Team Member 2 | 75 |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | 9.5 | 19 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 123.5 | 0 | 0 | 5700 | 11400 | 11400 | 11400 | 11400 | 11400 | 11400 | 0 | 0 | 0 | 74100
Team Member 3 | 80 |  |  |  | 0.5 | 1 | 1 | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 9.5 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 85.5 | 0 | 0 | 0 | 6080 | 12160 | 12160 | 12160 | 12160 | 0 | 0 | 0 | 0 | 54720
Technical Team | 90 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 19 | 19 | 38 | 38 | 38 | 57 | 57 | 57 | 38 | 38 | 38 | 38 | 475 | 13680 | 13680 | 27360 | 27360 | 27360 | 41040 | 41040 | 41040 | 27360 | 27360 | 27360 | 27360 | 342000
Training and Support
Team Members | 90 | [7 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 76 | 76 | 76 | 76 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54720 | 54720 | 54720 | 54720 | 54720 | 273600
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total FTEs |  | 3 | 3 | 4.5 | 5.5 | 6 | 7 | 7 | 11 | 9 | 8 | 8 | 8 | 57 | 57 | 85.5 | 104.5 | 114 | 133 | 133 | 209 | 171 | 152 | 152 | 152 | 1520 | 44080 | 44080 | 63460 | 75240 | 81320 | 95000 | 95000 | 149720 | 123880 | 112480 | 112480 | 112480 | 1109220 | Planned Value by month
| Workdays/Month | 19 | Note: Organizations will often have a standard # of workdays to use in project planning.
| Hours/day | 8
ACTUAL
|  | Months | [11 empty] | Workdays Jan: Workdays | Cost
|  | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Total
Resource/Role | Resource Cost/Hr | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Workdays | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Cost
Project Management
Project Manager | 125 | 0.5 | [11 empty] | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500
Team Members | 75 | 1 | [11 empty] | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11400
Software Development
Team Member 2 | 75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team Member 3 | 80 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Team | 90 | 1 | [11 empty] | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 13680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13680
Training and Support
Team Members | 90 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total FTEs |  | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 34580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34580 | Actual Cost by Month
| Workdays/Month | 19 | Note: Organizations will often have a standard # of workdays to use in project planning.
| Hours/day | 8
VARIANCE |  | -0.5 | -3 | -4.5 | -5.5 | -6 | -7 | -7 | -11 | -9 | -8 | -8 | Ç

## Sheet2 (hidden)
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898